## 01 RAG Summary
PMO GOVERNANCE DASHBOARD — WEEKLY PACK
Run Date: 07 April 2026 11:01 ¦ Portfolio: 20 Projects
| Total Projects | 🔴 RED | 🟡 AMBER | 🟢 GREEN | Portfolio Variance
| 20 | 7 | 6 | 7 | +3.6%
Project ID | Project Name | Owner | RAG | Budget Variance % | Schedule (Days) | Risk Score | Status
PRJ001 | ERP Enhancement 1 | James T | AMBER | +9.5% | 2 | 1.9 | On Hold
PRJ002 | ERP Enhancement 2 | Tom B | AMBER | -7.8% | 11 | 3.2 | On Hold
PRJ003 | API Development 3 | Emma R | RED | +13.7% | 19 | 4.9 | In Progress
PRJ004 | Cloud Migration 4 | Sarah K | GREEN | -11.9% | -2 | 1.5 | Complete
PRJ005 | API Development 5 | Kate S | GREEN | -12.4% | 4 | 4.5 | In Progress
PRJ006 | Analytics Dashboard 6 | Emma R | RED | +10.5% | -3 | 6.2 | In Progress
PRJ007 | Platform Upgrade 7 | Kate S | GREEN | -8.1% | 3 | 4.3 | Complete
PRJ008 | ERP Enhancement 8 | David L | AMBER | +0.3% | 3 | 5.4 | In Progress
PRJ009 | Digital Transformation 9 | Anandi M | RED | +11.6% | 7 | 0.8 | On Hold
PRJ010 | ERP Enhancement 10 | Emma R | GREEN | +0.1% | 3 | 1.5 | On Hold
PRJ011 | Data Migration 11 | James T | GREEN | -3.1% | -1 | 0.9 | In Progress
PRJ012 | ERP Enhancement 12 | Emma R | GREEN | +4.7% | 7 | 3.7 | In Progress
PRJ013 | API Development 13 | James T | AMBER | +7.5% | 12 | 5 | On Hold
PRJ014 | CRM Integration 14 | Raj P | RED | +16.5% | 23 | 6 | In Progress
PRJ015 | ERP Enhancement 15 | Sarah K | AMBER | +5.1% | -1 | 0.9 | In Progress
PRJ016 | Reporting Automation 16 | Sarah K | RED | +15.7% | 23 | 6.7 | Complete
PRJ017 | CRM Integration 17 | Priya M | RED | +9.2% | 21 | 1.1 | Complete
PRJ018 | Reporting Automation 18 | Emma R | RED | +13.8% | 8 | 7.3 | In Progress
PRJ019 | Digital Transformation 19 | Raj P | GREEN | -0.1% | 2 | 1 | Complete
PRJ020 | API Development 20 | James T | AMBER | +8.4% | -4 | 2.3 | In Progress